## R03
CSPC C1 Migration/POD2 MAS Project Implementation Schedule
Project | Milestone | Product | Type | Work Type | Finish Time | 2019 | [7 empty] | 2020
[6 empty] | Nov |  |  |  | Dec |  |  |  | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  | Apr |  |  |  | May |  |  |  | Jun |  |  |  | Jul |  |  |  | Aug |  |  |  | Sep
[6 empty] | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
POD2 | M0 |  |  | FDS | 2019-12-31 | bar: Nov W3 to Dec W4
| M1/M2 |  |  | DCS(CS) | 2019-04-15 | bar: Jan W4 to Apr W2
| M1 | SC56-16S | Truck | FAT | 2020-05-15 | Jan W4: 085FIQ631(A-872)新增 085FIQ641(A-873)新增; Apr W3: 联调; May W1: FAT; Jun W3: SAT
|  |  | Ship | FAT | 2020-05-15 | Jan W4: 088FIQ006(A-882)利旧; Apr W3: 联调; May W1: FAT; Jun W3: SAT
| M2 | ED28-200 | Drumming | FAT | 2020-05-15 | Jan W4: 085FIQ504(A-861)利旧; Apr W3: 联调; May W1: FAT; Jun W3: SAT
|  | ED56-200 | Drumming | FAT | 2020-05-15 | Jan W4: 085FIQ502(A-863)利旧; Apr W3: 联调; May W1: FAT; Jun W3: SAT
| M3 | SP30-45 | Truck | SAT | 2020-06-30 | Apr W1: 085FIQ621(A-621)新增; Jun W3: SAT
|  | MD22-40 | Truck | SAT | 2020-06-30 | Apr W1: 085FIQ624(A-624)新增; Jun W3: SAT
|  | MD36-13 | Truck | SAT | 2020-06-30 | Apr W1: 085FIQ506(A-862)利旧; Jun W3: SAT
|  | SA34-05 | Truck | SAT | 2020-06-30 | Apr W1: 085FIQ511(A-867)利旧; Jun W3: SAT
|  | MC28-02 | Truck | SAT | 2020-06-30 | Apr W1: 085FIQ503(A-864)利旧; Jun W3: SAT
|  | MD36-21 | Truck | SAT | 2020-06-30 | Apr W1: 085FIQ505(A-865)利旧; Jun W3: SAT
|  | ED28-200 | Truck | SAT | 2020-06-30 | Apr W1: 085FIQ504(A-861)利旧; Jun W3: SAT
|  | ED56-200 | Truck | SAT | 2020-06-30 | Apr W1: 085FIQ502(A-863)利旧; Jun W3: SAT
|  | SC56-16S | Truck | SAT | 2020-06-30 | Apr W1: 085FIQ501(A-860)利旧; Jun W3: SAT
|  |  | Truck | SAT | 2020-06-30 | Apr W1: 085FIQ512(A-866)利旧; Jun W3: SAT
|  | SA34-05 | Ship | SAT | 2020-06-30 | Apr W1: 088FIQ702(A-702)新增; Jun W3: SAT
|  | MC28-02 | Ship | SAT | 2020-06-30 | Apr W1: 088FIQ703(A-703)新增; Jun W3: SAT
|  | SP30-45 | Drumming | SAT | 2020-06-30 | Jun W3: SAT
|  | MD22-40 | Drumming | SAT | 2020-06-30 | Jun W3: SAT
|  | MD36-13 | Drumming | SAT | 2020-06-30 | Jun W3: SAT
|  | SA34-05 | Drumming | SAT | 2020-06-30 | Jun W3: SAT
|  | MC28-02 | Drumming | SAT | 2020-06-30 | Jun W3: SAT
| M4 | SM | Truck | SAT | 2020-09-30 | Jul W1: 085FIQ611(A-871)新增
|  |  | OTF | SAT | 2020-09-30 | Jul W1: 088FIQ701(A-701)新增
|  |  | Ship | SAT | 2020-09-30 | Jul W1: 088FIQ004(A-896)
1. For the sake of Coronavirus outbreak, extend M0, M1,M2 to 4.15 to 5.15 at site, conduct FAT
2. M3 SAT complete date to Jun. 30th.
3. According to the latest project schedule, DMC will start up at July 1st. And Prodution in Tank at July 30th.
Note on C8: xudong.yang: Plan to have FAT with SAT together at site to save time
Note on C10: xudong.yang: Plan to have FAT with SAT together at site to save time

## R02
CSPC C1 Migration/POD2 MAS Project Implementation Schedule
Project | Milestone | Product | Type | Work Type | Finish Time | 2019 | [7 empty] | 2020
[6 empty] | Nov |  |  |  | Dec |  |  |  | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  | Apr |  |  |  | May |  |  |  | Jun |  |  |  | Jul |  |  |  | Aug |  |  |  | Sep
[6 empty] | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
C1 Migrate |  |  | OTF | SAT | 2019-12-05 | bar: Nov W1 to Dec W1
|  |  | Ship | FAT | 2019-12-05 | bar: Dec W1
|  |  | Ship | SAT | 2020-01-10 | bar: Dec W1 to Jan W1
POD2 | M0 |  |  | FDS | 2019-12-31 | bar: Nov W3 to Dec W4
|  |  |  | DCS(CS) | 2019-01-23 | Nov W3: DCS Hardware Ready(春节前)
| M1 | SC56-16S | Truck | SAT | 2020-02-29 | Dec W2: 085FIQ631(A-872)新增 085FIQ641(A-873)新增
|  |  | Ship | SAT | 2020-02-29 | Dec W2: 088FIQ006（A-882)利旧
| M2 | ED28-200 | Drumming | SAT | 2020-03-31 | Jan W4: 085FIQ504(A-861)利旧
|  | ED56-200 | Drumming | SAT | 2020-03-31 | Jan W4: 085FIQ502(A-863)利旧
| M3 | SP30-45 | Truck | SAT | 2020-06-30 | Apr W1: 085FIQ621(A-621)新增
|  | MD22-40 | Truck | SAT | 2020-06-30 | Apr W1: 085FIQ624(A-624)新增
|  | MD36-13 | Truck | SAT | 2020-06-30 | Apr W1: 085FIQ506(A-862)利旧
|  | SA34-05 | Truck | SAT | 2020-06-30 | Apr W1: 085FIQ511(A-867)利旧
|  | MC28-02 | Truck | SAT | 2020-06-30 | Apr W1: 085FIQ503(A-864)利旧
|  | MD36-21 | Truck | SAT | 2020-06-30 | Apr W1: 085FIQ505(A-865)利旧
|  | ED28-200 | Truck | SAT | 2020-06-30 | Apr W1: 085FIQ504(A-861)利旧
|  | ED56-200 | Truck | SAT | 2020-06-30 | Apr W1: 085FIQ502(A-863)利旧
|  | SC56-16S | Truck | SAT | 2020-06-30 | Apr W1: 085FIQ501(A-860)利旧
|  |  | Truck | SAT | 2020-06-30 | Apr W1: 085FIQ512(A-866)利旧
|  | SA34-05 | Ship | SAT | 2020-06-30 | Apr W1: 088FIQ702(A-702)新增
|  | MC28-02 | Ship | SAT | 2020-06-30 | Apr W1: 088FIQ703(A-703)新增
|  | SP30-45 | Drumming | SAT | 2020-06-30 | bar: Apr W1 to Jun W4
|  | MD22-40 | Drumming | SAT | 2020-06-30 | bar: Apr W1 to Jun W4
|  | MD36-13 | Drumming | SAT | 2020-06-30 | bar: Apr W1 to Jun W4
|  | SA34-05 | Drumming | SAT | 2020-06-30 | bar: Apr W1 to Jun W4
|  | MC28-02 | Drumming | SAT | 2020-06-30 | bar: Apr W1 to Jun W4
| M4 | SM | Truck | SAT | 2020-09-30 | Jul W1: 085FIQ611(A-871)新增
|  |  | OTF | SAT | 2020-09-30 | Jul W1: 088FIQ701(A-701)新增
|  |  | Ship | SAT | 2020-09-30 | Jul W1: 088FIQ004(A-896)
Note on C11: xudong.yang: Plan to have FAT with SAT together at site to save time
Note on C13: xudong.yang: Plan to have FAT with SAT together at site to save time

## Schedule
Tasks |  |  | MileStone | M1/M2 |  |  |  | M3 | [16 empty] | M4
|  |  | Product | SC56-16S |  | ED28-200 | ED56-200 | SP30-45 | MD22-40 | MD36-13 | SA34-05 | MC28-02 | MD36-21 | ED28-200 | ED56-200 | SC56-16S |  | SA34-05 | MC28-02 | SP30-45 | MD22-40 | MD36-13 | SA34-05 | MC28-02 | SM
|  |  | Type | Truck | Ship | Drumming | Drumming | Truck | Truck | Truck | Truck | Truck | Truck | Truck | Truck | Truck | Truck | Ship | Ship | Drumming | Drumming | Drumming | Drumming | Drumming | Truck | OTF | Ship
|  |  | FAT Finish Time | 2020-5-11 to 2020-5-25(Test Function) |  |  |  | June
Module | Title |  | SAT Finish Time | June
CS | Control Drawing Programming
| A | Sebol Programming for Truck loading |  | DONE | DONE | DONE | DONE | DONE | DONE | DONE | DONE | DONE | DONE | DONE | DONE | DONE | DONE | INPROG | INPROG | DONE | DONE | DONE | DONE | DONE | NOTSTARTED | NOTSTARTED | NOTSTARTED
| B | Sebol Programming for Ship loading |  | DONE | DONE | DONE | DONE | DONE | DONE | DONE | DONE | DONE | DONE | DONE | DONE | DONE | DONE | INPROG | INPROG | DONE | DONE | DONE | DONE | DONE | NOTSTARTED | NOTSTARTED | NOTSTARTED
| C | Sebol Programming for Drumming |  | DONE | DONE | DONE | DONE | DONE | DONE | DONE | DONE | DONE | DONE | DONE | DONE | DONE | DONE | INPROG | INPROG | DONE | DONE | DONE | DONE | DONE | NOTSTARTED | NOTSTARTED | NOTSTARTED
| D | Logic Programing for Truck loading |  | DONE | DONE | DONE | DONE | DONE | DONE | DONE | DONE | DONE | DONE | DONE | DONE | DONE | DONE | INPROG | INPROG | DONE | DONE | DONE | DONE | DONE | NOTSTARTED | NOTSTARTED | NOTSTARTED
Graphic
| E | Graphic for Truck loading |  | DONE | DONE | DONE | DONE | DONE | DONE | DONE | DONE | DONE | DONE | DONE | DONE | DONE | DONE | INPROG | INPROG | DONE | DONE | DONE | DONE | DONE | NOTSTARTED | NOTSTARTED | NOTSTARTED
| F | Graphic for Ship Loading |  | DONE | DONE | DONE | DONE | DONE | DONE | DONE | DONE | DONE | DONE | DONE | DONE | DONE | DONE | INPROG | INPROG | DONE | DONE | DONE | DONE | DONE | NOTSTARTED | NOTSTARTED | NOTSTARTED
| G | Graphic for Drumming |  | DONE | DONE | DONE | DONE | DONE | DONE | DONE | DONE | DONE | DONE | DONE | DONE | DONE | DONE | INPROG | INPROG | DONE | DONE | DONE | DONE | DONE | NOTSTARTED | NOTSTARTED | NOTSTARTED
MS | Master Data
| 1 | Tank master data configuration
| 2 | Tank Inventory configuration (from TDAS?)
| 3 | Product master data configuration
| 4 | Path Configuration
| 5 | New loading bay, arm configuration
| 6 | Get the Tank inventory data for new tanks
SAP Interface
| 7 | Modify the interface with SAP |  | NA | NA |  |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | INPROG | INPROG | INPROG | INPROG | INPROG | NA | NA | NA
Order loading Procedure for New bay
| 8 | Tap card at New Bay
| 9 | Cancel order at New bay
| 10 | Start Loading from New bay
| 11 | Suspend loading from New bay
| 12 | Loading Finish (Batch End)from New bay
Integration Testing
| 13 | Integration Testing with SAP
| 14 | Integration Testing with DCS
FAT
SAT